## Sheet1
Snake |  |  | Start 13 May | Finish 26 July
Scale: | weeks
Duration: | 10
Task | Start | Duration | Finish
Initial Canvas prototypes | 0 | 1 | 1
Outline Requirements | 1 | 1 | 2
Storyboard | 1 | 1 | 2
Snake Prototype | 2 | 1 | 3
Mouse input | 3 | 4 | 7
Problem Definition | 6 | 1 | 7
Buttons | 6 | 4 | 10
Menu system | 6 | 4 | 10
Sound | 6 | 3 | 9
Score | 6 | 4 | 10
Attatch prototypes | 9 | 1 | 10
Graphics | 9 | 1 | 10
Test Game | 9 | 1 | 10